## Sheet1
| Team 1 | Team 2 | Team 3
Technical Architect | Kevin | David P | Matt
Product | Abilgail + Quality | Kyle | Ryan M
UX Designer | Franklin | Ryan C | Alana
Front End Developer | Kat | Brandon | Anthony
Middleware + Database | David S, Simon | Enrique | Ricky
Quality |  | Gregory | Chris
| Responsibility |  |  | Types of questions you should focus on
Technical Architect | Designing overall software architecture, training team as needed |  |  | Which software do we use? How does the database communicate with the software?
Product | Designing overall functional use cases |  |  | Which pages do we have?
UX Designer | Designing look and feel of the app |  |  | How does the application look? Build the application styles and string xmls
Front End Developer | Implementing look and feel of the app |  |  | Build the application xmls
Middleware + Database | Implementing the software & database of the application |  |  | Build the activity and database code
Quality | Developing test cases and running the tests |  |  | Build the test scripts and run them. If they do not pass, inform team what did not pass

## Sheet2
|  | Start of Class | End of Class
2018-04-16 | Requirements & Design
| Technical Architect |  | Database Diagrams
| Product |  | Document all required pages
| UX Designer |  | Wireframes
| Front End Developer |  | Blank XML Layout for all pages
| Middleware + Database |  | Blank Activities for all pages
| Quality |  | none
2018-04-23 | Build
| Technical Architect | Source Control setup, Determine required technologies (communication, database) | Deliver all remaining interfaces (e.g. middle ware to db layer)
| Product | Document page flow, Document individual page functionality
| UX Designer | 10 of each piece of data, Final Page Mockups | Xml Styles completed
| Front End Developer | Initial android skeleton for all pages (no coding)
| Middleware + Database | Database layer completed, some non-ui logic
| Quality | Document initial test cases, Investigate automated testing
2018-04-30 | Build
| Technical Architect | Support middleware team with final touches
| Product | Support UX and testing team with final touches
| UX Designer | All images assets, styles delivered
| Front End Developer | Deliver all pages visually | Deliver all pages functionally
| Middleware + Database | Deliver all pages functionally
| Quality | Finish all detailed test cases and share with team. | Run first test and generate test report
2018-05-07 | Test & Deploy
| Technical Architect | General bug fixes | General bug fixes
| Product | General bug fixes | General bug fixes
| UX Designer | none
| Front End Developer | General bug fixes | General bug fixes
| Middleware + Database | General bug fixes | General bug fixes
| Quality | Deliver any automated testing scripts. Test entire application, deliver test report. | Test entire application, deliver final test report.
2018-05-14